## Sheet1
Story ID | Story Name | Description | Priority | Iteration number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
E02 | Open Account | As a customer, I want to open account through providing accurate personal information, so that I can use other functions provided by the bank. | 1 | 1 | • Verity that the customer must provide four types of information: name, address, date of birth and type of account to be opened. • Verity that the customer should be issued a personal identification number (PIN) for their own account. • Verity that when a customer open the account, they are required to choose an account type. | After opening an account,each account will have a unique accountID a default PIN(their birthday). | 2019-03-05 | 2019-03-11
E02a | Confirm Credit History | As a bank employee, I want update customer credit status as satisfactory once I receive the conformation from credit agency following a credit check, so that I can carry on to open the account. | 1 | 1 | • Verify that customer exists in system matching details given. | / | 2019-03-05 | 2019-03-11
E08 | Record Modifications | As an manager, I want to record all kinds of modification of customers' account as soon as possible, so that I can make sure there is no loss of my bank. | 1 | 1 | • Verify that after depositing or withdrawing the funds, the account should be updated immediately and make sure there is no money loss. • Verify that make sure changes are synchronized with the latest operations of the account. | / | 2019-03-05 | 2019-03-11
E08a | Record Opening Account | As a manager of the bank, I want to record the new opened account of all customers | 1 | 1 | • Make sure all the modification is valid | / | 2019-03-05 | 2019-03-11
E03 | Deposit Funds | As a depositor (who may not be the account holder), I want to enter the details of the account to be credited and the amount of funds to be deposited, so that I can deposit the funds to the account. | 1 | 2 | • Verity that before depositing funds, the customer should provide the appropriate account number. • Verity that after depositing funds,the condition of funds should be either cleared or uncleared. | Cleared funds are immediately credited to the account. | 2019-03-12 | 2019-03-20
E03a | Verify Numeric Input | As an employe of the bank, I want to check whether the amout is entered in a valid format.(digital or decimal) | 1 | 2 | • Verify that customer enters a number. | / | 2019-03-12 | 2019-03-20
E04 | Clear Funds | As an external bank clearing system, I want periodically clears un-cleared funds, so that the funds are credited to the account | 3 | 2 | • Make sure the bank clearing system updating the cleared condition in time. | / | 2019-03-12 | 2019-03-20
E04a | Verify the account ID and PIN | As a manager of the bank, I want to check whether the account ID and PIN is correct before the customer clearing funds, withdrawing funds, suspend account and close account. | 1 | 2 | • Make sure the PIN matches the account ID |  | 2019-03-12 | 2019-03-20
E08b | Record Depositing Funds | As a manager of the bank, I want to update the record after depositing funds. | 1 | 2 | • Make sure all the modification is valid | / | 2019-03-12 | 2019-03-20
E08c | Record Clearing Funds | As a manager of the bank, I want to update the record after clearing funds. | 1 | 2 | • Make sure all the modification is valid | / | 2019-03-12 | 2019-03-20
E05 | Withdraw Funds | As a customer, I want to supply my account number, the correct PIN, and the amount to be withdrawn, so that I can withdraw funds from my account. | 1 | 3 | • Verity that only by providing correct account number, an appropriate identification and the appropriate amount of money to be withdrawn can the customers withdraw their funds. • Verity that the customer cannot withdraw more funds than their limit permits. • Verity that for a withdrawal from a Saver account, a minimum period of notice must be given before any withdrawal can be made. | • In the case of Junior and Saver accounts, no withdrawal should result in a negative balance. • In the case of a Current account, a customer may withdraw additional funds which is up to but not exceeding their overdraft limit. | 2019-03-21 | 2019-04-25
E05a | Notice Withdrawal | As a customer, I want to supply my account number, the correct PIN, and the amount to be withdrawn, so that I can send a notice before withdrawing. | 1 | 3 | • Make sure the account is noticed after noticing. | • If the customer provide inapproprate personal information, the account can't be noticed. | 2019-03-21 | 2019-04-25
E05b | Check Notice | As an employe of the bank, I want to check whether the account had been noticed before the withdrawl. | 1 | 3 | • Make sure the account is noticed before withdrawal. | • If the withdrawal has not been noticed, the customer won't be able to withdraw. | 2019-03-21 | 2019-04-25
E05c | Check the Withdrawal Amount | As an employe of the bank, I want to check whether the account has enough balance and overdraft limit for the withdrawl. | 1 | 3 | • Verity that the customer cannot withdraw more funds than their limit permits. | • In the case of Junior and Saver accounts, no withdrawal should result in a negative balance. • In the case of a Current account, a customer may withdraw additional funds which is up to but not exceeding their overdraft limit. | 2019-03-21 | 2019-04-25
E08d | Record Withdrawing Funds | As a manager of the bank, I want to update the record after withdrawing funds. | 1 | 3 | • Make sure all the modification is valid | / | 2019-03-21 | 2019-04-25
E06 | Suspend Account | As a customer, I want to suspend my account, so that no more transactions may occur until the account is reinstated. | 5 | 4 | • Verity that the accounts that have already been suspended should not do any transactions until it has reinstated by the customer. • Verity that when the customer reinstates the account,customers have to provide the accurate account number. | The customer should enter the correct account number and correct PIN to suspend the account. | 2019-04-26 | 2019-05-05
E07 | Close Account | As a customer, I want to close my account, so that I can save resources for me and for the bank. | 5 | 4 | • Verity that before the account closes, the system should make sure that the balance has been cleared. | The customer should enter both the correct account number and PIN to close the account. | 2019-04-26 | 2019-05-05
E08e | Record Suspending Account | As a manager of the bank, I want to update the record after suspending account. | 1 | 4 | • Make sure all the modification is valid | / | 2019-04-26 | 2019-05-05
E08f | Record Closing Account | As a manager of the bank, I want to update the record after closing account. | 1 | 4 | • Make sure all the modification is valid | / | 2019-04-26 | 2019-05-05
E01 | User Manual | As a manager, I want that the system has clear instructions to teach the customer how to use it, so that I won’t need employees to help them and save resources. | 1 | 5 | • Verify that each step should have a readable instruction which can be understood by any customer. | / | 2019-05-06 | 2019-05-11
E01a | Account Introduction | As a customer, I want to know which type of accounts I should open, so that I can choose the most suitable account. | 1 | 5 | • Verity that there are three types of accounts(saver account, junior account and current account) for you to see clearly and choose. • Verity that a customer may open more than one type of accounts. | Junior account should be opened that only customers are under the age of 16. | 2019-05-06 | 2019-05-11
E01b | Bank Sysytem Introduction | As a customer, I want to see the functions provided by the bank clearly, so that I can choose the service I want. | 1 | 5 | • Verity that there are six choices(open account, deposit funds, clear funds, withdraw funds, suspend account, close account)for you to see clearly and choose. • Verity that only after opening accounts, the customers can select other functions provided by bank . | / | 2019-05-06 | 2019-05-11